## Tool
Guidance for the development of CEJST Tree Maintenance and Planting Project
*We have used the Objective Buidling Tool to illustrate all the Deliverables List by Practice/Activitys, Descriptions and Objective Statements for use developing your Work Plan, Budget and application. *There are 3 Phases and depending on the scope of work of your project and your capacity this could take 1, 2 or 3 years to complete. *Use the Objective #s from the respective 1 - 3 year completion schedule column to complete your Work Plan and Budget. *For 2 year projects, you will use the 1-year Objectives numbers for the Objectives you plan to complete in year 1.
Deliverables List by Practice/Activity | Description | Order of Completion | Objective #s 3-year duration | Objective #s 2-year duration | Objective #s 1-year duration | Objective Statements
Phase 1
Practice Plan | Secure project team and review/refine the project schedule. | 1 | 1 | 1 | 1 | The project team is secured, kick off meeting(s) are held, a project schedule and urban forestry standards and specificationsis are adopted by the end of quarter 1.
Public Tree Ordinance | Adopt/Review the public tree ordianceconsistent NCFS U&CF and Arbro Day Foundation templates and update as necessary/applicable. | 1 |  |  |  | Review/update/adopt the urban forestry/public tree ordinance by quarter ? (as applicable)
Urban Forestry Standards and Specifications Document | Develop standards and specifications document. These specifications will be used to bid for and complete inventory, tree mainteance and planting work. NCFS U&CF has templates. | 2
Complete Tree Inventory | Develop and complete bidding and awarding for services processes. | 3 | 2 | 2 | 2 | Develop tree inventory and outreach services request for services, advertise, award and secure contracts for services by the end of quarter ?.
Tree Inventory Tools | Professional tree inventory software or suitable inventory data management application to plan, complete and report on the completion of tree workand planting. | 4
Outreach Program | Develop and complete bidding and awarding for services processes for work that will be completed by a extgernal service provider. | 5
Outreach Program | Develop outreach program. Events and products that will be developed and schedule. Note, be sure to include products to inform the public on the project and when tree work is scheduled in their area. | 6 | 3 | 3 | 3 | Develop outreach program plan, products and the outreach/media campaign and inform and engage the public about/in the project by the end of quarter ?.
Outreach Products | Develop/publish outreach products identified in the Outreach Progam plan. | 7
Outreach Event | Media campaign, product delivery or event to as specified in the Outreach Program Plan notify the public about the project and the inventory work that will be starting | 8
Complete Tree Inventory | Consultant completes tree inventory and a fundings report, activates tree inventory software and provides training. Staff monitors completion of work. | 9 | 4 | 4 | 4 | Complete the tree inventory, report and tree maintenance plan by the end of quarter ?.
Practice Plan | Develop tree maintance plan based on the inventory detailing work schedule and secure estimates to complete the tree work. | 10
Outreach Event | Media campaign, outreach product delivery or event as specified in the Outreach Program Plan celebrating the completion of the tree inventory and planting and post care plans project. | 11 | 5 | 5 | 5 | The outreach products/media campagin/outreach events celebrating phase 1 completion is/are delivered/completed by the end of quarter ?.
Phase 2
Tree Maintenance | Develop and complete bidding and awarding processes for tree maintenance services. | 1 | 1 | ? | 6 | Develop tree mainteance request for services, advertise, award and secure contracts for services by the end of quarter ?.
Practice Plan | Develop and complete bidding and awarding processes for consulting services to develop the Tree Planting and Post Care Plans | 2 | 1
Outreach Event | Media campaign, outreach product delivery or event to notify the public about the start of tree mainteance | 3 | 2 | ? | 7 | The outreach products/media campagin/outreach events is/are delivered/completed by the end of quarter ?.
Tree Maintenance | Monitor, approve, and complete tree mainteance | 4 | 3 | ? | 8 | The tree maintenance and Tree Planting and Post Care Plans are completed by the end of quarter ?
Practice Plan | Develop Tree Planting and Post Care Plans and cost estimates | 5 | 3
Outreach Event | Media campaign, outreach product delivery or event to celebrating the completion of the tree mainteance project. | 6 | 4 | ? | 9 | The outreach products/media campagin/outreach events celebrating phase 2 completion is/are delivered/completed by the end of quarter ?.
Phase 3
Tree Planting | Develop and complete bidding and awarding processes for tree supply and planting services | 1 | 1 | ? | 10 | Develop tree planting and post planting mainteance request for services, advertise, award and secure contracts for services by the end of quarter ?.
Tree Maintenance | Develop and complete bidding and awarding processes for tree watering and mainteance services | 2 | 1
Outreach Event | Media campaign, outreach product delivery or event to notify the public about the start of tree planting | 3 | 2 | ? | 11 | The outreach products/media campagin/outreach events is/are delivered/completed by the end of quarter ?.
Tree Planting | Inspect and approve trees, monitor planting and complete tree planting | 4 | 3 | ? | 12 | The tree planting project is completed by the end of quarter ?
Outreach Event | Media campaign, outreach product delivery or event to celebrating the completion of the project. | 6 | 4 | ? | 13 | The outreach products/media campagin/outreach events celebrating phase 3 completion is/are delivered/completed by the end of quarter ?
Tree Maintenance | Complete/monitor tree watering and mainteance | 5 | 5 | ? | 14 | Post planting tree care plan is completed by the end of quarter ?

## Task Lists from Work Plan
Task Lists for Practices/Activities for reference/use
Inventories & Assessments |  | Ordinances | Outreach | Plans
Develop profesional services request for proposal |  | Develop profesional services request for proposal | Program Plan | Develop profesional services request for proposal
Advertise RFP |  | Advertise RFP | Outreach Products | Advertise RFP
Review & Award RFP |  | Review & Award RFP | Secure Venue | Review & Award RFP
Secure services contract |  | Contract Development | Secure Speakers | Contract Development
Secure Project Committee |  | Secure Development Committee | Market Event | Secure Development Committee
Project Kick Off Meeting |  | Stakeholder Survey | Program Registration | Stakeholder Survey
Complete/Monitor Work |  | Development Meeting 1 | Hold Event | Development Meeting 1
Draft 1 Data & Report received |  | Draft 1 | Program Assessment/Review | Draft 1
Draft 1 Review Complete |  | Draft 1 Review Complete |  | Draft 1 Review Complete
Development Meeting 2 |  | Development Meeting 2 |  | Development Meeting 2
Final Draft received |  | Final Draft |  | Final Draft
Final Draft Review |  | Final Draft Review |  | Final Draft Review
Development Meeting 3 |  | Development Meeting 3 |  | Development Meeting 3
Final Draft Complete |  | Final Draft Complete |  | Final Draft Complete
Outreach Products |  | Outreach Products |  | Outreach Products
Outreach Event |  | Outreach Event |  | Outreach Event
Tree Maintenance |  | Tree Planting
Outreach products to inform stakeholders of work |  | Outreach products to inform stakeholders of work
Outreach event to solicit and obtain buyin |  | Outreach event to solicit and obtain buyin
Tree Inventory/Map |  | Tree Planting Site Inventory/Map
Program Plan |  | Tree Planting & Post Care Plan
Tree Mainentance Specifications | Contracting | Develop profesional services request for proposal
Develop profesional services request for proposal |  | Advertise RFP
Advertise RFP |  | Review & Award RFP
Review & Award RFP |  | Contract Development
Contract Development |  | Secure Delivery Site & Tree Care
Outreach Event |  | Order Trees
Project Kick Off Meeting |  | Order Supplies
Complete/Monitor Work |  | Order Tools
Quality Assurance Inspection |  | Secure Watering
Confirm Suppiles Delivery
Outreach Event
Mark Planting Sites
Utility Stake Outs
Planting Site Adjustments
Deliver Supplies to Site
Site Preparation Complete
Complete/Monitor Work
Quality Assurance Inspection

## DDs & Defintions
Advocacy Group Development | Organization Strategic Plan Development | Fees for professional planning firm to facilitate and publish a strategic plan.
Education & Training
Programs | Education/Training Program Plan | Development of education or training program.
| Volunteer Stewardship Program Plan | Development of a long-term, sustainable community volunteer U&CF stewardship program.
| Workforce Development Program Plan | Development of a long-term, sustainable urban and community forestry job training program.
Practices & Activities | Education/Training Products | Training and educational publications and media products.
| Education/Training Event | Development and delivery of educational or training event.
| Education/Training Tools | PPE and tools required to complete the education or training event or program.
| Professional Certifications | Attend training and acquire a U&CF professional credential.
Inventories & Assessments | Tree Canopy Cover Assessment | A tree canopy cover assessment uses aerial photographs and other types of remote sensing data to quantify the area of a community covered by tree canopy, vegetation, hardscape and other land cover features for planning purposes. The assessment also quantifies the ecosystem services provided by the tree canopy.
| Urban Heat Island Assessment | Assessment and analysis using remote sensing data and on the ground surveys will identify UHI areas from which mitigation strategies such as tree planting can be developed.
| Program Assessment/Review | A formal review of an organization or program policies and practices to identify opportunities for organizational design improvement.
| Complete Tree Inventory | An inventory of all trees and planting sites located on community street right-of-ways and/or community properties.
| Partial Tree Inventory | A partial tree inventory records trees or sites that meet a specific management objective. Examples include a risk tree inventory, tree planting site inventory or an inventory of trees with forest health issue.
| Project Tree Inventory | An inventory of all trees located within a project area.
| Sample Tree Inventory | A statistically valid sample inventory of trees in a community or defined area in the community. The resulting data will provide estimates of numbers of trees, tree species, condition, age and management needs for planning purposes.
| Stakeholder Survey | Surveys of stakeholders to solicit comment and or identify issues and needs for strategic planning and implementation.
| Tree Inventory Tools | Computer software to house, maintain and manage a tree inventory. Data collection devices and other tree inventory tools.
Outreach | Outreach Program | Development of an outreach program.
| Outreach Event | Development and delivery of an outreach event.
| Outreach Products | Outreach publications and media products.
| Stakeholder Survey | Surveys of stakeholders to learn urban and community forestry knowledge, needs and/or engage in an outreach, educational or training event.
Ordinances, Policy, Standards & Specifications | Conservation Development Ordinance | An ordinance that directs tree and other natural resource conservation during development.
| Historic/Legacy Tree Ordinance | An ordinance that provides protection for individual trees of historical significance.
| Landscaping Ordinance | An ordinance that specifies landscaping requirements for existing properties or properties under development.
| Public Tree Ordinance | An ordinance that establishes municipal authority over the management of public trees and sets management policy and standards. All Tree City USA communities or communities working toward Tree City USA status must have a public tree ordinance.
| Urban Forestry Standards and Specifications Document | Policy, standards, and specifications document to guide and the planting, maintenance, removal and protection of community trees.
Plans | Community Forestry Plan | A plan that guides the development and implementation of community wide or specific community forestry activities.
| Practice Plan | A plan that establishes objectives, specifications, policy and a budget that addresses a single urban forestry practice in the management of the community's urban forest. The primary audience is the staff and leadership of the organization. Examples include food forest plan, a risk tree mitigation plan, a tree maintenance plan, a tree planting and post-care plan or an urban wood utilization plan.
| Management Plan | A comprehensive plan that establishes policies, goals, objectives and a budget for the operational management of the community's urban forest. The primary audience is the staff and leadership of the organization.
| U&CF Comprehensive Plan | A comprehensive plan that establishes policies, goals, and objectives for all U&CF activities for the management of the community's urban forest. The audience is the public, staff, and leadership of the community.
Tree Maintenance | Tree Maintenance | Completion of a tree maintenance project; watering, pruning, removal etc.
| Tree Maintenance Tools | Pruners, saws and other arboricultural diagnostic and maintenance tools and equipment.
Tree Planting | Tree Planting | Completion of the tree planting.
| Tree Planting Site Preparation | Removal of poor soil, asphalt or concrete to establish suitable growing conditions for the species of tree to be planted.
| Tree Planting Tools and Supplies | Tools, mulch, staking supplies and watering bags.